## Slide 1: Agile Software Development (DIT191 / EDA397)
Lecture 3: Agile methods crash course
Eric Knauss
<eric.knauss@cse.gu.se>

## Slide 2: Experience Agile
Cockburn calls this a miniature
  One hour to do two XP iterations
Facilitate and discuss concepts
Help team building
Info taken from http://c2.com/xp/ExtremeHour.html

## Slide 3: Divide your group
Choose a product
  Family spaceship
  Mosquito hunter
Our new product must dominate the corporate sector of the well established spaceship / mosquito market
Plan, schedule, develop and quality assure our initial release
Project timeframe: One Hour!
1-2 Onsite customer
4 developer (2 pairs)
1 QA
1 Tracker

## Slide 4: Sixty Minute Project
10 Minutes User Stories & Arch. Spike
10 Minutes estimate Priority & Scope
10 Minutes init Commitment Schedule
10 Minutes Iteration 1
10 Minutes fix Commitment Schedule
10 Minutes Iteration 2
Release!

## Slide 5: Rules
If It Ain't Drawn, It Ain't Delivered.
If It Ain't Written On A Napkin, It Ain't UserStory/FunctionalTest(ed).
Presenter plays Coach
QA can't see what developers draw till end of 10 minutes.
Developers don't know what QA or Stakeholders write until end of 10 minutes.
Tracker gives 5 minute and last minute warnings.

## Slide 6: User Stories & Arch. Spike
Onsite customers write User Stories
Developres draw architectural spike
Everybody else walks around and suggests things  facilitate information flow

## Slide 7: Estimate Priority & Scope
Stakeholders sort Stories into 3 piles:
  Must Have
  Costly To Lose
  Nice To Have
Stakeholders rank relative priorities within each pile.
Meanwhile 4 Developers assign Ideal Minute costs to Stories based on Spike experience
  Use max story size 10 ideal minutes, or else make Stakeholders split/clarify.
  Optimism wins. But Note Risks.

## Slide 8: Initial Commitment Schedule
Schedule stories into 2 Iterations.
Schedule priority & risk first.
Use Initial Load Factor 3
  This means there are 4 x 10 = 40 Real minutes; 40/3 = 13 Ideal Minutes per Iteration using initial load factor.

## Slide 9: Iteration 1
QA writes down Functional Tests for each Story
QA can't see what developers draw until end of Iteration.
Then QA "runs" tests, notes bugs.
Meanwhile Developers define engineering tasks.
Developers draw solutions
If other developers can't understand a drawing, it fails unit test.
Developers should refactor where they can
Tracker notes any deletions
Onsite customers secretly think up new stories, the evil bastards.
Notes:   Run Tests: Any story with bugs is incomplete and affects subsequent Load Factor.
Define engineering tasks: This is to say, the developers talk about things that have to be drawn to enable them to satisfy the user stories. Generally they seemed to plan for about 10 seconds before drawing.

## Slide 10: Fix Commitment Schedule
Tracker or coach measures real velocity and modifies ideal minute size of second iteration
Turn QA bugs into Stories
Reveal Stakeholders' new Stories
Prioritize & Scope all Stories
Fit Stories into Schedule, possibly replacing previous ones

## Slide 11: Iteration 2
QA writes down Functional Tests for each Story
QA can't see what developers draw until end of Iteration.
Then QA "runs" tests, notes bugs.
Meanwhile Developers define engineering tasks.
Developers draw solutions
If other developers can't understand a drawing, it fails unit test.
Developers should refactor where they can
Tracker notes any deletions
Onsite customers secretly think up new stories, the evil bastards.
Notes:   Run Tests: Any story with bugs is incomplete and affects subsequent Load Factor.
Define engineering tasks: This is to say, the developers talk about things that have to be drawn to enable them to satisfy the user stories. Generally they seemed to plan for about 10 seconds before drawing.

## Slide 12: Release!
Stakeholders determine if this is an external release - is it marketable?
If you're not exhausted, reschedule stories that didn't make it in this release ...